## Project Proposal
Project proposal
Objectives
- Demonstate the real-time application using SignalR
Project background
- Since I have a chance to research the SignalR and share it with other associates, I would like to make a small project to show how SignalR is applied in reality.
- With this project, I hope that it helps to understand more about how signalR works
Proposed solution
Create an web chat application with basics functionalities but have to apply the signalR to make it become a real-time application.
Requirements
Register, login, logout
View/Update user's account
Add friends
Create conversations
Send messages
View contact's profile
Required points
User can register an account in the web application
User can login in the web application
User can view/update their profile
User can view other account names which are registered in the web application
User can add new contact in their contact list
User can view new contact's profile
Open points
User can create a conversation
User can create a conversation with their contact (2 participants in a conversation)
User can update the conversation information
User can send a message to a conversation that they participated
Project timline
| April | May |  |  |  | June |  |  |  | July
| W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13
Requirement Analysis | bar: April W1 to May W2
System Analysis
Implementation |  |  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10
Testing | bar: W8 to W10
Deployment | bar: W10
Operations

## Requirement Gathering
Requirement Gathering
Business process modeling
1. Define and describe actors
User: | register, login, logout
add new contact, view contact's profile
udpate user profile
create conversations, update conversation's profile that the user participated
send messages to the conversation that user participated
Contact: | can show as online if user's account is logging or offline when user's account is logout
can be added to a contact list of any users
Conversation: | has many messages from one or many contacts
has conversation profile, and can be updated by participants
2. Glossary
| Name | Explaination
1 | User | User is the one who has the account to login and use the functionalities of the system.
2 | Contact | An user is added to another user's contact list is a contact.
3 | Conversation | where stores messages of participants in the conversation
4 | Message | text will be sent to the conversation by the user ( or participant in conversation context)
3. Use cases
Use case: Register an account
1. User access web application by browser
2. User filles the register form and submit
3. System will check the input:
3.1 If all fields are valid, an account will be created
3.2 If any field is invalid, system will inform cannot create an account because the field is not valid
Use case: Login
1. User access web application by browser
2. Input username and password in the login form
3. System will check the input:
If the account is existed, it will navigate to home page
If the account is not existed, it will inform username or password is not valid
Use case: Update user profile
1. User access web application by browser
2. User login
3. User go to profile page
4. User update profile by inputing fields
5. System will check the input:
5.1 If all fields are valid, profile updated successfully
5.2 If any field is invalid, system will inform cannot update because the field is not valid
Use case: Add new contact
1. User access web application by browser
2. User login
3. Click add new contact
If added successfully, the new contact will immediately show in user contact list
If added unsuccessfully, inform user that can not add new contact

## Requirement Analysis
Requirement Analysis
1. Define classes
User
Contact
Conversation
Message
Participant
Role
2. Class relationship
Inheritance
Association
Aggregation
Composition

## Implementation
Implementation
1. Main tasks |  | 2. Planned timeline |  |  | 3. Real timeline
1 | Database | W1 | W3 (08/05 - 14/05) | 1, 2.1 | W1 | W3 (08/05 - 14/05) | 1,2.1
2 | CRUD of all tables | W2 | W4 (15/05 - 21/05) | 2.2, 2.3 | W2 | W4 (15/05 - 21/05) | Register + Login UI, Login return token
| 2.1 User, Role, User Contact | W3 | W5 (22/05 - 28/05) | 3 | W3 | W5 (22/05 - 28/05) | - Create components: users, contacts, profile - Add intercepter (Frontend) - Show contacts, show suggestions, profile - Upload avatar and store at ImageKit (Backend)
| 2.2 Conversation, Participants | W4 | W6 (29/06 - 04/06) | 4 | W4 | W6 (29/06 - 04/06) | - Upload Avatar in Frontend - View suggestions profile, update UI suggestion list - Update profile
| 2.3 Message | W5 | W7 (05/06 - 11/06) | 5, 6, 7 | W5 | W7 (05/06 - 11/06) | - Initialized hub in server and connect from client
3 | Register UI + call API | W6 | W8 (12/06 - 18/06) | 8 | W6 | W8 (12/06 - 18/06) | - [Front-end] Add Auth Guard - Create First Message (include first conversation, participants)
4 | Login UI + call API | W7 | W9 (19/06 - 25/06) | 8 | W7 | W9 (19/06 - 25/06) | - [Backend] Get conversations, conversationById, Mesesages in Conversation Planned: - Create front end for the above BE functions - Create message in a conversation
5 | Logout | W8 | W10 (26/06 - 02/07) | 9 | W8 | W10 (26/06 - 02/07) | [Front-end]: Get conversations, send message, show messages [Back-end]: APIs for send message, update get conversations, re-arrange codes Planned: - Conversation in details - UI for conversation - Apply hubs
6 | View profile UI + call API | W9 | W11 (03/07 - 09/07) | 9 | W9 | W11 (03/07 - 09/07)
7 | Update profile UI + call API | W10 | W12 (10/07 - 16/07) | 10 | W10 | W12 (10/07 - 16/07)
8 | Show contacts + Add new contact into user contact list
9 | Send message
10 | Update conversation

## Sheet1
First message
| Message | Create conversation
| Id | Create ConverstaionParticipant | conversationid | userId
ConversationParticipantId
| Content | Create Message | ConversationId | Content
Conversation
Id
Name
ConversationParticipant
Id
ConversationId
UserId

## Libraries
Frontend
https://www.npmjs.com/package/@angular-material-components/datetime-picker
https://stackblitz.com/edit/angular-material-button-spinner?file=app%2Fbutton-types-example.html

## Sheet2
Content of SignalR presentation.